## Sheet1
Risk Identification |  |  | Risk Response
Risk | Risk Score | Risk Ranking | Risk Response | Trigger | Risk Owner
Tidak Memenuhi Kebutuhan pengguna | 8 | High | Risk Mitigation | Kurangnya pengumpulan persyaratan pengguna yang komprehensif | Project Manager
Keterbatasan sumber daya dalam proyek | 7 | medium | Risk Mitigation | Keterlambatan Pemberian dukungan dan sumber daya kurang memadai | Project Manager
Keamanan data yang buruk | 9 | High | Risk Mitigation | Serangan kemanan yang berhasil dan kerugian data | IT Security Team
ketidaksesuaian regulasi | 6 | Medium | Risk Avoidance | Perubahan peraturan dan kebijakan terkait PPID | Legal Team ( Dinas PPID )
gangguan teknis | 7 | Medium | Risk Mitigation | Gangguan sistem infrastruktur yang menyebabkan error atau waktu terhenti | IT Support Team
Key Terms
Risk: The risk stated in a complete sentence which states the cause of the risk, the risk, and the effect that the risk causes to the project.
Risk Category: Categorization of risks by area of project affected, source of risk or other useful category.
Probability: The likelihood that a risk or opportunity will occur (on a scale from 0 to 10 with 10 being the highest).
Impact: The impact of the risk on the project if the risk occurs (scale from 0 to 10 with 10 being the highest).
Risk Score: Determined by multiplying probability and impact (scale from 0 to 100).
Risk Ranking: A priority list which is determined by the relative ranking of the risks (by their scores) within the project with the number one being the highest risk score.
Risk Response: The action which is to be taken if this risk occurs.
Trigger: Something which indicates that a risk is about to occur or has already occured.
Risk Owner: The person who the project manager assigns to watch for triggers, and manage the risk response if the risk occurs.
This Risk Register Template is brought to you by www.projectmanagementdocs.com